## Week 1
SR NO | RefNo | Activity | Efforts | Description | From | To | TaskId | Task | Resource | Priority
| 1 | Registration
BD001 | 1.1 | Design Signup Form(Razor) | 0.25
BD002 | 1.2 | Client Side JavaScript input validations | 0.16
BD003 | 1.3 | Add registration action method in user controller | 0.08
BD004 | 1.4 | Implement registration Logic in user repository | 0.25 | User creation and by default User status ENABLE=FALSE
BD005 | 1.5 | Check User Exist | 0.08
BD006 | 1.6 | Implement Mobile API | 6 | Efforts Dependency with resources allocation
| 1.7 | Generate OTP (Unique) | 1
| 1.8 | Send OTP to Mobile | 1
| 1.9 | Design OTP entry Form (Razor) | 0.25
| 1.10 | Add RESEND OTP button in OTP Entry Form | 0.08
| 1.11 | Client Side OTP Verification | 0.25
| 1.12 | Check OTP AGE | 0.08 | Expiry
| 1.13 | Update User Subscription | 0.08 | User status ENABLE=TRUE
| 2 | Login
| 2.1 | Design Login Form(Razor) | 0.16
| 2.2 | Client Side JavaScript Input validations | 0.16
| 2.3 | http Post action method in user controller | 0.08
| 2.4 | Implement Login Logic in user repository | 0.25
| 2.5 | Redirect to Home | 0.25
| 2.6 | Design Home Form | 0.15
| 3 | Logout
| 3.1 | Add Logout Button in Home Repository | 0.08
| 3.2 | Implement Logout Logic in User repository | 0.16