## Week 1
RefNo | Activity | Efforts | Description | From | To | TaskId | Task | Resource | Priority
1 | SignUp
1.1 | Design Signup Form(Razor) | 1 |  |  |  | TS001 | Design Signup Form(Razor)
1.2 | Client Side JavaScript input validations | 1 |  |  |  | TS002 | Client Side JavaScript input validations
1.3 | Add registration action method in user controller | 0.5 |  |  |  | TS003 | Add registration action method in user controller
1.4 | Implement registration Logic in user repository | 2 | User creation and by default User status ENABLE=FALSE |  |  | TS004 | Implement registration Logic in user repository
1.5 | Check User Exist | 0.5 |  |  |  | TS005 | Check User Exist
1.6 | Generate Email Confirmation Link - SEND- RECEIVE- Email Expiry | 8 |  |  |  | TS006 | Generate Email Confirmation Link
1.10 | Design User Activation Page (Razor) | 0.5 |  |  |  | TS007 | Design User Activation Page (Razor)
1.11 | Update User Subscription | 0.5 | User status ENABLE=TRUE |  |  | TS008 | Update User Subscription
1.12 | Send Email Acknowledgement | 1 |  |  |  | TS009 | Send Email Acknowledgement
2 | Login
2.1 | Design Login Form(Razor) | 0.5 |  |  |  | TS001 | Design Login Form(Razor)
2.2 | Client Side JavaScript Input validations | 0.5 |  |  |  | TS002 | Client Side JavaScript Input validations
2.3 | Method in user controller to handle Login | 0.5 |  |  |  | TS003 | http Post action method in user controller
2.4 | Implement Login Logic in user repository | 0.5 |  |  |  | TS004 | Implement Login Logic in user repository
2.5 | Redirect to Home | 0.5 |  |  |  |  | Redirect to Home
2.6 | Design Home Form | 1 |  |  |  | TS005 | Design Home Form
3 | Logout
3.1 | Add Logout Button in Home | 0.5 |  |  |  |  | Add Logout Button in Home
3.2 | Implement Logout Logic in User Controller | 0.5 | Session.Abandon() |  |  | TS001 | Implement Logout Logic in User repository
4 | Change Password
4.1 | Design ChangePassword Form(Razor) | 0.5 |  |  |  | TS001 | Design ChangePassword Form(Razor)
4.2 | Client Side JavaScript Input validations | 0.5 |  |  |  | TS002 | Client Side JavaScript Input validations
4.3 | Validate Old Password | 0.5 |  |  |  | TS003 | Validate Old Password
4.4 | Add UpdatePassword action method in user controller | 0.5 |  |  |  | TS004 | Use UpdatePassword action method From user controller
4.5 | Update New Password in DB | 0.5 |  |  |  | TS005 | Update New Password in DB
4.6 | Send Email Acknowledgement | 0 |  |  |  |  | Send Email Acknowledgement
5 | Forgot Password
5.1 | Design ForgotPassword Form(Razor) | 0.5 |  |  |  | TS001 | Design ForgotPassword Form(Razor)
5.2 | Client Side JavaScript Input validations | 0.5 |  |  |  | TS002 | Client Side JavaScript Input validations
5.3 | Use UpdatePassword action method in user controller | 0 |  |  |  |  | Add UpdatePassword action method in user controller
5.4 | Generate Email Confirmation Link | 0 | Use Email Confirmation Logic form Registration Logic in user Repository |  |  |  | Generate Email Confirmation Link
5.5 | Design Enter New Password Page | 0.5 |  |  |  | TS003 | Design Enter New Password Page
5.6 | Update New Password in DB | 0 |  |  |  |  | Update New Password in DB
5.7 | Send Email Acknowledgement | 0 |  |  |  |  | Send Email Acknowledgement