## Efforts
Phase | Stage | Estimate
Inception | Create architecture concept | 8
| Create alternative concept #1 | 16
| Create alternative concept #2 | 16
Elaboration | Create prototype | 8
| Develop design prototype #1 | 8
| Develop design prototype #2 | 8
| Develop design prototype #3 | 8
Construction | Implement Activity 1 | 36
| Implement Activity 2 | 64
| Implement Activity 3 | 182
| Implement Activity 4 | 72
| Implement Activity 5 | 64
| Implement Activity 6 | 56
| Implement Activity 7 | 8
| Implement Activity 8 | 48
| Implement Activity 9 | 24
Transition | Documentation development | 16
| Release | 16
| TOTAL: | 658

## Activity
RefNo | Activity | TaskId | Task | Efforts | Description
1 | Authentication |  |  | 36
|  | 1.1 | Login | 16
|  | 1.2 | Logout | 8
|  | 1.3 | Change Password | 4
|  | 1.4 | Forgot Password | 8
2 | DashBoard |  |  | 64
|  | 2.1 | Add User Link | 4 | Link to Open 3.1
|  | 2.2 | Show Total users Count | 4
|  | 2.3 | Add Billing Link | 4 | Link to 6.6
|  | 2.4 | Show Today biilling Amount | 4
|  | 2.5 | Add Transaction Link | 4 | Link to 3.8
|  | 2.6 | Show Today Transactions Amount | 4
|  | 2.7 | Add Commission Link | 4 | Link to 6.5
|  | 2.8 | Show Today Commission Earned | 4
|  | 2.9 | Add Payment requests Link | 4 | Link to 6.7
|  | 2.1 | Show today payment requests count | 4
|  | 2.11 | Add Support Tickets Link | 4 | Link to 8.2
|  | 2.12 | Show Open Ticket Count | 4
|  | 2.13 | List Last 5 transaction | 8
|  | 2.14 | List Last 5 billing history | 8
3 | Manage Customer |  |  | 182
|  | 3.1 | Add User/Customer | 24 | You can create user by using user regsitration form or ugrade any user to retailer or distributor through retailer or distributor tabs.
|  | 3.2 | Retailer Role | 4 | For making a retailer, first you need to create a user, then by using retailer tab you can upgrade that user to retailer. Befor making retailer you also need to create commission packages, provided in setting menu.
|  | 3.3 | Distributor Role | 4 | For making a Distributor, first you need to create a user, then by using distributor tab you can upgrade that user to retailer. Befor making Distributor you also need to create commission packages, provided in setting menu.
|  | 3.4 | List Users | 8 | All registered users will appear here.
|  | 3.5 | Retailers | 8 | List retailer users with Action > manage
|  | 3.6 | In Retailers, Manage Action to Edit Profile | 4
|  | 3.7 | In Retailers, Manage Action to View Credits | 8
|  | 3.8 | In Retailers, Manage Action to Credit Amount | 16
|  | 3.9 | In Retailers, Manage Action to Debit Amount | 16
|  | 3.1 | In Retailers, Manage Action to Change password | 8
|  | 3.11 | In Retailers, Manage Action to View Commission | 8
|  | 3.12 | Distributors | 8 | List distributor users
|  | 3.13 | In Distributors, Manage Action to Edit Profile | 4
|  | 3.14 | In Distributors, Manage Action to View Credits | 2
|  | 3.15 | In Distributors, Manage Action to Credit Amount | 2
|  | 3.16 | In Distributors, Manage Action to Debit Amount | 2
|  | 3.17 | In Distributors, Manage Action to Change password | 2
|  | 3.18 | In Distributors, Manage Action to View Commission | 2
|  | 3.19 | In Distributors, Manage Action to Set Activation Fee | 16 | You can set Retailer Activation Fee, by sharing profit between admin (you) & your distributor. Total fee (Retailer Activation Fee) will be charged/deducted from distributor's balance & at the same time profit will be shared to distributor and admin.
|  | 3.2 | List All Users | 8 | List users with Roles, balance, status
|  | 3.21 | Manage All users | 16 | Edit users
|  | 3.22 | Credit | 2 | Credit Amount
|  | 3.23 | Debit | 2 | Debit Amount
|  | 3.24 | List Transactions | 8 | List Credit & Debit Transactions
4 | Settings |  |  | 72
|  | 4.1 | Payment Options | 8 | Here you can add bank name with account number. These bank details will appear to your direct client's update payment form. In the same way you will receive the payment request. It will help you to track the bank in which your client has made payments.
|  | 4.2 | Flash News | 8 | Flash news will allow you to place instant news/alerts to your direct downline partners. News will scroll on header part above menu. ON/OFF
|  | 4.3 | Banners | 16 | Banners will appear as pop up when your downline partner login to his panel. You can also specify user type, to whom you wish to notify through panel.
|  | 4.4 | Set Commission | 16 | You can modify/Update your client's commission from here. Whenever you modify commission package, you need to set commission. Only modification in commission package will not update to user/users package.
|  | 4.5 | Commission package - Create | 16 | Here you can create new packages or modify your existing package. After modification, you need to assign/set that package to perticular user. Define "My Profit" for different operators given below and Update.
|  | 4.6 | Commission package - Edit | 8
5 | Branding |  |  | 64
|  | 5.1 | General Settings | 16
|  | 5.2 | Page Settings | 16 | Home page data
|  | 5.3 | Slider Settings | 16 | Home page slider
|  | 5.4 | Mobile landing Page Settings | 16 | Logo & landing Text
6 | Accounts |  |  | 56
|  | 6.1 | Edit profile | 8
|  | 6.2 | Change Password & PIN | 8
|  | 6.3 | Login Details | 8
|  | 6.4 | My Commission | 8
|  | 6.5 | Commission Earned Report | 8
|  | 6.6 | Billing Summary | 8
|  | 6.7 | Payment requests | 8
7 | Download Applications |  |  | 8
|  | 7.1 | Android | 4
|  | 7.2 | Iphone | 4
8 | Support |  |  | 48
|  | 8.1 | Create Ticket | 16
|  | 8.2 | List Tickets | 8
|  | 8.3 | List Disputes | 8 | For any dispute your retailer can raise dispute tickets by providing transaction ID. These tickets will be responded by our support team. You can view the status and details by using "DETAILS" button.
|  | 8.4 | Update Payment | 8 | Update Bank Account Details
|  | 8.5 | List Payment History | 8
9 | Master page |  |  | 24
|  | 9.1 | Header with logo | 8
|  | 9.2 | Header with Login Name | 4
|  | 9.3 | Header with Balance Amount | 4
|  | 9.4 | Header with logout button | 4
|  | 9.5 | Footer with Copyright | 4